## Instructions
Instructions for Managers. If you have questions, please ask.
0 | The majority of the feedback for this lab will be given throughout the duration of the lab period
1 | Additionally, some feedback will be integrate in subsequent labs.
2 | Feedback and grades are not the same thing, and do not necessarily align.
3 | The values generated by this rubric do not constitute as your grade.
4 | This rubric is meant to be a guide to give you a sense of how your lab will be scored and as a tool to help the Instructor and TA grade these. It is easy for us to miss the work you have done, so this is designed to prevent us from overlooking items.
5 | The cells you and your teammates fill out are green
6 | The cells that the instructor and TA will fill out are yellow
7 | Do not modify the cells that are grey
8 | Complete the 'Summary" sheet first
9 | The 'Tasks' sheet is essentially the task sheet you already have, plus a 'completed' column. Fill that column at a minimum. Additionally, it will help if you fill the 'actual' efforts (use your best estimate). Including filenames/tags/branches/hashes for variants/attempts/refinements
10 | Fill out the 'attendance' sheet.
11 | Every week you will update and upload this task sheet along with a brief update slide that will note changes/updates/concerns/questions for the TA and Instructor.
12 | At the end of the lab session you will submit this task sheet
13 | The following day managers will submit an evaluation of the team. Additionally, each member will submit their own self-assesment.
14 | The TA/Instructor will fill out the 'effort' sheet from your teams individual assessments. We will validate and adjust the points in the 'tasks' sheet. Adjust the 'attendance' against our record to generate your individual lab grade.

## Summary
Notes: | 1 | Fill out only the green cells
Team Name (your choice): | something
Team Number/Letter (what is on canvas): | 6
Start Date: | 2025-03-04
End Date:
Number of Members: | 5
| Name (first last) | Email | Alternate Contact
Member A Name (Manager): | Luis Guillen | luis.a.guillen.arcos-1@ou.edu
Member B Name (Tech Lead): | Madylin Teel | madylin.d.teel-1@ou.edu
Member C Name: | An Vu | an.vu@ou.edu
Member D Name: | Coleman Bixler | colemanbixler@ou.edu
Member E Name: | Nathan Stephani | nathanstephani12@ou.edu
Member F Name: | Garrett Snow | garrett.w.snow-1@ou.edu
Link for cloning the repository |  | Note: gitlab has limits on the number of members to of members on a private repository. Right now this link only needs to be accessible to the team.
Date Submitted
Days Early | 0
Days Late | 0
Stats for the lab
| Member A | Member B | Member C | Member D | Member E | Member F
Hours spent in class | 11 | 9 | 11 | 12 | 12 | 12
Hours spent outside of class | 0 | 35 | 0 | 0 | 0 | 0
Subtotals | 11 | 44 | 11 | 12 | 12 | 12
Total Person Hours | 102
| Est | INST/TA Est
Raw Team Scores [points] | 820 | 0
Min Score (<=4 person) [points] | 984
Min Score (5 person) | 1230
Min Score (6 person) | 1476
Total Lab Days | 12 |  | NOTE:The days during spring vacation will be "freebies".
Missed Day Penalty (actual grade points [0..100]) | 8.3333
Manager Bonus (actual grade points [0..100]) | 25
Tech Lead Bonus (actual grade points [0..100]) | 25
Thresholds per person (not including manager/tech lead bonus or missed day penalties) | 100% | 90% | 80% | 70%
Points needed per person (<=4 person team) | 246 | 221.4 | 196.8 | 172.2
Points needed per person (5 person team) | 243 | 218.7 | 194.4 | 170.1
Points needed per person (6 person team) | 243 | 218.7 | 194.4 | 170.1

## Tasks
[8 empty] | Team member's % to task (final after task is done) | [5 empty] | Est Start Date | Est end | Act Start Date | Act End Date | Est Start Day (Day=1 first day of lab) | Est Duration | Actual Start Day (Day=1 first day of lab) | Actual duration |  | Important: tag/branch/file (how do we find this (these) file(s) in your repository and evaluature them if applicable). [req] | Completed [req] | Estimated Raw Score | INST/TA Completed
Task (Manager is the lead, but may delegate) | Points Required | Points Optional | Task Name (Only bold tasks are required, everything else is for extra points) | Description | Task Goal | Notes | Lead | A | B | C | D | E | F | [10 empty] | (1=complete, .5=substantial attempt, 0=not attempted)
| 5 |  | Communication | Establish a primary and backup methods of communication. | Each team member has redundant channels for the team. |  | 1 | [6 empty] | 2025-03-04 | 2025-03-05 | 2025-03-04 | 2025-03-04 | 1 | 1 | 1 | 0 | 72 |  | 1 | 5 | 0 | 0
| 5 |  | Version Control System | Create a common gitlab repository for the team and push the code. | Each member can clone, push to, and pull from the repository. Verify this ASAP |  | 1 | [6 empty] | 2025-03-04 | 2025-03-05 | 2025-03-04 | 2025-03-04 | 1 | 1 | 1 | 0 | 73 |  | 1 | 5 | 0 | 0
| 5 |  | Configure IDE | Configure environment on everyone's system (vscode remote ssh to gpel machines). | Each member can clone/push/pull to the repository. |  | 1 | [6 empty] | 2025-03-04 | 2025-03-05 | 2025-03-04 | 2025-03-04 | 1 | 1 | 1 | 0 | 74 |  | 1 | 5 | 0 | 0
| 5 |  | Initial Build | Make sure that everyone can execute the code on their system. | Everyone can build and run the code |  | 1 | [6 empty] | 2025-03-04 | 2025-03-05 | 2025-03-04 | 2025-03-04 | 1 | 1 | 1 | 0 | 75 |  | 1 | 5 | 0 | 0
| 5 |  | Review Lab Document | Identify the goals, tasks, and points of confusion in the document. | Generate questions for the instructor to clear ambiguity. |  | 1 | [6 empty] | 2025-03-04 | 2025-03-06 | 2025-03-04 | 2025-03-06 | 1 | 2 | 1 | 2 | 76 |  | 0 | 0 | 0 | 0
| 5 |  | Initial Statement of Work (wk 1) | A living document assigning high-level tasks to the team | Brief description in repository README.md of who will work on what (high level). Include outside of class meeting times here. |  | 1 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-11 | 1 | 7 | 1 | 7 | 77 |  | 0 | 0 | 0 | 0
| 5 |  | One page slide (wk 1) | This slide will help guide discussion with TA/Instructor during in class lab time. | A brief slide with updates, questions, and changes. |  | 1 | [6 empty] | 2025-03-04 | 2025-03-11 |  |  | 1 | 7 | #NUM! | 0 | 78 |  | 0 | 0 | 0 | 0
| 5 |  | Tasksheet (wk 1) | Initial version of this sheet, with current attendance filled in. | A mapping of tasks to individuals |  | 1 | [6 empty] | 2025-03-04 | 2025-03-11 |  |  | 1 | 7 | #NUM! | 0 | 79 |  | 0 | 0 | 0 | 0
| 5 |  | One page slide (wk 2) | This slide will help guide discussion with TA/Instructor during in class lab time. | A brief slide with updates, questions, and changes. |  | 1 | [6 empty] | 2025-03-11 | 2025-03-18 | 2025-03-11 | 2025-03-18 | 8 | 7 | 8 | 7 | 80 |  | 1 | 5 | 0 | 0
| 5 |  | Tasksheet (wk 2) | update version of this sheet, with current attendance filled in. | A mapping of tasks to individuals |  | 1 | [6 empty] | 2025-03-11 | 2025-03-18 | 2025-03-11 | 2025-03-18 | 8 | 7 | 8 | 7 | 81 |  | 1 | 5 | 0 | 0
| 5 |  | One page slide (wk 3) |  |  |  | 1 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 82 |  | 0 | 0 | 0 | 0
| 5 |  | Tasksheet (wk 3) |  |  |  | 1 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 83 |  | 0 | 0 | 0 | 0
| 5 |  | One page slide (wk 4) |  |  |  | 1 | [6 empty] | 2025-03-25 | 2025-04-01 | 2025-03-25 | 2025-03-25 | 22 | 7 | 22 | 0 | 84 |  | 1 | 5 | 0 | 0
| 5 |  | Tasksheet (wk 4) |  |  |  | 1 | [6 empty] | 2025-03-25 | 2025-04-01 | 2025-03-25 | 2025-03-25 | 22 | 7 | 22 | 0 | 85 |  | 1 | 5 | 0 | 0
| 5 |  | Update final statement of work | updated readme.md of SoW |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-01 | 2025-04-08 | 29 | 7 | 29 | 7 | 85 |  | 1 | 5 | 0 | 0
| 5 |  | Submit final codebase | git bundle of all branches tarballed and submitted to canvas |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-09 | 2025-04-09 | 29 | 7 | 37 | 0 | 85 |  | 1 | 5 | 0 | 0
| 5 |  | Submit final document | final document uploaded |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-09 | 2025-04-09 | 29 | 7 | 37 | 0 | 85 |  | 1 | 5 | 0 | 0
|  | 5 | submit additional material | Notes, meeting minutes, and other additional artifacts that you believe will be useful for grading. |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 85 |  | 0 | 0 | 0 | 0
| 5 |  | Submit final tasksheet | The final version of this sheet, to be used by the TA/Instructor. | Completed tasksheet with claimed points validated. |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-09 | 2025-04-09 | 29 | 7 | 37 | 0 | 85 |  | 1 | 5 | 0 | 0
| 5 |  | Submit team assessment | Post assessement of the team. Submitted the day after the other deliverables. |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-09 | 2025-04-09 | 29 | 7 | 37 | 0 | 86 |  | 1 | 5 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 87 |  | 0 | 0 | 0 | 0
Task (Tech Lead is the owner, but tasks may be delegated) | Points Required | Points Optional | Task Name | Description | Task Goal | Notes (please list filename where this is implemented ) | [11 empty] | #NUM! | 0 | #NUM! | 0 | 88
[18 empty] | #NUM! | 0 | #NUM! | 0 | 89 |  | 0 | 0 | 0 | 0
Technical Document | 15 |  | Initial Outline for technical writeup | Initial sketch of how the team will approach the objectives |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-11 |  |  | 1 | 7 | #NUM! | 0 | 90 |  | 1 | 15 | 0 | 0
| 15 |  | Working Draft (wk 2) | Draft of the sketch. This should be sufficiently fleshed out with the designs such that the team can use this to proceed on the objectives |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 91 |  | 1 | 15 | 0 | 0
| 15 |  | Updated Working Draft (wk 3) | Updated of previous draft |  |  | 2 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 92 |  | 1 | 15 | 0 | 0
| 15 |  | Updated Working Draft (wk 4) | Updated of previous draft |  |  | 2 | [6 empty] | 2025-03-25 | 2025-04-01 |  |  | 22 | 7 | #NUM! | 0 | 93 |  | 0 | 0 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 94 |  | 0 | 0 | 0 | 0
Directory, Driver Scripts, and Building |  | 20 | .gitlab-ci.yml | Create a CI/CD pipeline that runs all tests every time code is pushed. |  |  | 2 | [10 empty] | #NUM! | 0 | #NUM! | 0 |  |  | 0 | 0 | 0 | 0
|  | 20 | deploy runners on OU resources | You will be given access to virtualized resources where you can deploy runners. |  |  | 2 | [10 empty] | #NUM! | 0 | #NUM! | 0 |  |  | 0 | 0 | 0 | 0
| 10 |  | Implement directory structure for lab | ./lab/objectives/XXObjectiveXX/XXTasksXX/ |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 |  |  | 1 | 10 | 0 | 0
| 10 |  | Implement top-level driver scripts that runs all objective scripts | ./lab/objectives/{run-all-verify.x,run-all-measure.x,clean-all.x} |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 |  |  | 1 | 10 | 0 | 0
| 10 |  | Implement Objective-level driver scripts that run all tasks scripts | ./lab/objectives/objective-{a,b,c,d,e}/{run-all-verify.x,run-all-measure.x,clean-all.x} |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 |  |  | 1 | 10 | 0 | 0
|  |  |  | ./lab/objectives/objective-{a,b,c,d,e}/{run-all-verify.x,run-all-measure.x,clean-all.x} |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 |  |  | 0 | 0 | 0 | 0
| 10 |  | Implement task-level driver scripts for objective a for running the code | ./lab/objectives/objective-a/{task00,task01,...}/{run-all-verify.x,run-all-measure.x,clean-all.x} |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 |  |  | 1 | 10 | 0 | 0
| 20 |  | Implement task-level driver scripts for objective b for running the generators and evaluating the resulting code | ./lab/objectives/objective-d/{task00,task01,...}/{run-all-verify.x,run-all-measure.x,clean-all.x} |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 |  |  | 1 | 20 | 0 | 0
| 20 |  | Implement task-level driver scripts for objective c for running the generators and evaluating the resulting code | ./lab/objectives/objective-c/{task00,task01,...}/{run-all-verify.x,run-all-measure.x,clean-all.x} |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 |  |  | 1 | 20 | 0 | 0
| 20 |  | Implement task-level driver scripts for objective d for running the generators and evaluating the resulting code | ./lab/objectives/objective-d/{task00,task01,...}/{run-all-verify.x,run-all-measure.x,clean-all.x} |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 |  |  | 1 | 20 | 0 | 0
| 20 |  | Implement task-level driver scripts for objective d for running the generators and evaluating the resulting code | ./lab/objectives/objective-e/{task00,task01,...}/{run-all-verify.x,run-all-measure.x,clean-all.x} |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-07 |  |  | 1 | 3 | #NUM! | 0 | 95 |  | 1 | 20 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 111 |  | 0 | 0 | 0 | 0
Objective B: Simple Standalone Generator | 15 |  | Design the baseline generator | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-11 |  |  | 1 | 7 | #NUM! | 0 | 112 |  | 1 | 15 | 0 | 0
| 5 |  | Design the baseline generator + unroll | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-11 |  |  | 1 | 7 | #NUM! | 0 | 113 |  | 1 | 5 | 0 | 0
| 5 |  | Design the baseline generator + split | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-11 |  |  | 1 | 7 | #NUM! | 0 | 114 |  | 1 | 5 | 0 | 0
| 5 |  | Design the baseline generator + interchange | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-04 | 2025-03-11 |  |  | 1 | 7 | #NUM! | 0 | 115 |  | 1 | 5 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 116 |  | 0 | 0 | 0 | 0
Objective C: EoC AST to C Code generator | 15 |  | Design the AST to C code generator | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 117 |  | 1 | 15 | 0 | 0
| 10 |  | Design and implement unit tests for AST to C code generator that cover 100% of your code. | Create a plan for testing and implement it before proceeding. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 118 |  | 0 | 0 | 0 | 0
| 5 |  | Implement and test AST node for: function |  |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 119 |  | 1 | 5 | 0 | 0
| 5 |  | Implement and test AST node for: loop |  |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 120 |  | 1 | 5 | 0 | 0
| 5 |  | Implement and test AST node for: assign to a variable and assign to memory location |  |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 121 |  | 1 | 5 | 0 | 0
| 5 |  | Implement and test AST node for: add, multiply and modulo |  |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 122 |  | 1 | 5 | 0 | 0
| 5 |  | Implement and test AST node for: less-than |  |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 123 |  | 1 | 5 | 0 | 0
Objective C: EoC Operation Specification to AST | 15 |  | Design the Objective Specification to AST functionality | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 124 |  | 1 | 15 | 0 | 0
| 10 |  | Design and implement unit tests for Operation Specification to AST | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 125 |  | 0 | 0 | 0 | 0
Objective C: EoC AST to AST Schedulers | 15 |  | Design the compiler pass (AST to AST) for implementing unroll | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 126 |  | 0 | 0 | 0 | 0
| 10 |  | Design the unit tests for the unroll pass | Create a plan for testing and implement it before proceeding. This should hit 100% coverage of the code you created. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 127 |  | 0 | 0 | 0 | 0
| 15 |  | Design the compiler pass (AST to AST) for implementing split | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 128 |  | 0 | 0 | 0 | 0
| 10 |  | Design the unit tests for the split pass | Create a plan for testing and implement it before proceeding. This should hit 100% coverage of the code you created. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 129 |  | 0 | 0 | 0 | 0
| 15 |  | Design the compiler pass (AST to AST) for implementing interchange | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 130 |  | 0 | 0 | 0 | 0
| 10 |  | Design the unit tests for the interchange pass | Create a plan for testing and implement it before proceeding. This should hit 100% coverage of the code you created. |  |  | 2 | [6 empty] | 2025-03-11 | 2025-03-18 |  |  | 8 | 7 | #NUM! | 0 | 131 |  | 0 | 0 | 0 | 0
Objective D: Complex AST to AST Scheduler | 15 |  | Design the generalized scheduler (AST to AST) | Specify this function in words and diagrams. Describe the input and output. Provide examples of how one could test this function. Finally, detail the pseudo-code for this operation. Do this in the design document. |  |  | 2 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 132 |  | 0 | 0 | 0 | 0
| 10 |  | Design the unit tests for the unroll pass using the generalized scheduler | Create a plan for testing and implement it before proceeding. This should hit 100% coverage of the code you created. |  |  | 2 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 133 |  | 0 | 0 | 0 | 0
| 10 |  | Design the unit tests for the split pass using the generalized scheduler | Create a plan for testing and implement it before proceeding. This should hit 100% coverage of the code you created. |  |  | 2 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 134 |  | 0 | 0 | 0 | 0
| 10 |  | Design the unit tests for the interchange pass using the generalized sheduler | Create a plan for testing and implement it before proceeding. This should hit 100% coverage of the code you created. |  |  | 2 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 135 |  | 0 | 0 | 0 | 0
| 10 |  | Design the unit tests for verifying complex (more than one transformation) schedules | Create a plan for testing and implement it before proceeding. This should hit 100% coverage of the code you created. |  |  | 2 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 136 |  | 0 | 0 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 137 |  | 0 | 0 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 138 |  | 0 | 0 | 0 | 0
Task | Points Required | Points Optional | Task Name | Description | Task Goal | Notes (please list filename where this is implemented ) | [11 empty] | #NUM! | 0 | #NUM! | 0 | 139
Teams tasks to be delegated by manager. | [17 empty] | #NUM! | 0 | #NUM! | 0 | 140 |  | 0 | 0 | 0 | 0
Objective A: Handspun | 5 |  | T00: Handspun Baseline | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications in SSA form. |  | The verification will be reflexive in that FILE_TST=FILE_REF | 1 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-11 | 1 | 7 | 1 | 7 | 141 |  | 1 | 5 | 0 | 0
| 5 |  | T01: Handspun + Unroll | Implement, Verify, Benchmark, and Compare for Five (5) of the Operation Specifications in SSA form. |  |  | 6 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-11 | 1 | 7 | 1 | 7 | 142 |  | 1 | 5 | 0 | 0
|  | 5 | T01-Opt00: Handspun + Unroll( r) vs Unroll ( q) | Implement, Verify, Benchmark, and Compare for One (1) Operation, but two (2) different loops in SSA form. |  |  | 6 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-11 | 1 | 7 | 1 | 7 | 143 |  | 1 | 5 | 0 | 0
| 5 |  | T02: Handspun + Split | Implement, Verify, Benchmark, and Compare for Five (5) of the Operation Specifications in SSA form. |  |  | 5 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-25 | 1 | 7 | 1 | 21 | 144 |  | 1 | 5 | 0 | 0
|  | 5 | T02-Opt00: Handspun + Split(i) vs Split (j) vs Split(q) vs Split( r) | Implement, Verify, Benchmark, and Compare for One (1) Operation, but four (4) different loops to be split in SSA form. |  |  | 5 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-25 | 1 | 7 | 1 | 21 | 145 |  | 1 | 5 | 0 | 0
|  | 5 | T02-Opt01: Handspun + Split(2) vs +Split(4) vs Split(8) | Implement, Verify, Benchmark, and Compare for One (1) Operation, One (1) loop, but four (4) different split factors) in SSA form. |  |  | 5 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-11 | 1 | 7 | 1 | 7 | 146 |  | 1 | 5 | 0 | 0
| 5 |  | T03: Handspun + Interchange | Implement, Verify, Benchmark, and Compare for One (1) Operation against six (6) different ways to interchange the loops in SSA form. | [9 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-11 | 1 | 7 | 1 | 7 | 147 |  | 1 | 5 | 0 | 0
| 5 |  | T04: Handspun + Complex Schedule (3 Commands) | Implement, Verify, Benchmark, and Compare for three (3) of the Operation Specifications using the same schedule in SSA form. |  |  | 3 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-11 | 1 | 7 | 1 | 7 | 148 |  | 1 | 5 | 0 | 0
|  | 5 | T04-Opt00: Handspun + Complex Schedule (3 Commands) | Implement, Verify, Benchmark, and Compare for one (1) of the Operation Specification using three (3) different schedules in SSA form. |  |  | 3 | [6 empty] | 2025-03-04 | 2025-03-11 | 2025-03-04 | 2025-03-11 | 1 | 7 | 1 | 7 | 149 |  | 0 | 0 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 150 |  | 0 | 0 | 0 | 0
Objective B: Simple Standalone Generator | 15 |  | T00: Simple Standalone Baseline | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications in SSA form. | [9 empty] | 2025-03-11 | 2025-03-18 | 2025-03-11 |  | 8 | 7 | 8 | #NUM! | 151 |  | 0 | 0 | 0 | 0
| 15 |  | T01: Simple Standalone + Unroll | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications for All relevant schedule specifications in SSA form. |  |  | 6 | [6 empty] | 0 | 1900-01-06 | 2025-03-11 |  | #NUM! | 7 | 8 | #NUM! | 152 |  | 1 | 15 | 0 | 0
| 15 |  | T01: Simple Standalone + Unroll v1 | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications for All relevant schedule specifications in SSA form. |  |  | 6 | [6 empty] | 2025-03-11 | 2025-03-18 | 2025-03-11 |  | 8 | 7 | 8 | #NUM! | 152 |  | 1 | 15 | 0 | 0
| 15 |  | T02: Simple Standalone + Split | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications for All relevant schedule specifications in SSA form. |  |  | 5 | [6 empty] | 2025-03-11 | 2025-03-18 | 2025-03-25 | 2025-03-27 | 8 | 7 | 22 | 2 | 153 |  | 1 | 15 | 0 | 0
| 15 |  | T03: Simple Standalone + Interchange | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications for All relevant schedule specifications in SSA form. |  |  | 4 | [6 empty] | 2025-03-11 | 2025-03-18 | 2025-03-11 |  | 8 | 7 | 8 | #NUM! | 154 |  | 1 | 15 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 155 |  | 0 | 0 | 0 | 0
Objective C: EoC Standalone Generator | 15 |  | T00: Implement AST to C codegen | Implement and test. | [9 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 156 |  | 0 | 0 | 0 | 0
| 15 |  | T01: Implement Operation Specification to AST | Implement and test. | [9 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 157 |  | 0 | 0 | 0 | 0
| 15 |  | T02: Implement the compiler pass (AST to AST) for implementing unroll | Implement and test. | [9 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 158 |  | 0 | 0 | 0 | 0
| 15 |  | T03: Implement the compiler pass (AST to AST) for implementing split | Implement and test. | [9 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 159 |  | 0 | 0 | 0 | 0
| 15 |  | T04: Implement the compiler pass (AST to AST) for implementing interchange | Implement and test. | [9 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 160 |  | 0 | 0 | 0 | 0
| 15 |  | T05: EoC Standalone Baseline | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications in SSA form. |  |  | 5 | [6 empty] | 2025-03-18 | 2025-03-25 | 2025-03-27 | 2025-04-03 | 15 | 7 | 24 | 7 | 161 |  | 1 | 15 | 0 | 0
| 15 |  | T06: EoC Standalone + Unroll | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications for All relevant schedule specifications in SSA form. |  |  | 6 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 162 |  | 1 | 15 | 0 | 0
| 15 |  | T07: EoC Standalone + Split | "" |  |  | 5 | [6 empty] | 2025-03-18 | 2025-03-25 | 2025-04-08 | 2025-04-08 | 15 | 7 | 36 | 0 | 163 |  | 1 | 15 | 0 | 0
| 15 |  | T08: EoC Standalone + Interchange | "" |  |  | 4 | [6 empty] | 2025-03-18 | 2025-03-25 |  |  | 15 | 7 | #NUM! | 0 | 164 |  | 1 | 15 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 165 |  | 0 | 0 | 0 | 0
Objective D: Complex Schedule Generator | 20 |  | T00: Implement Generalized Schedule (AST to AST) | Implement and test. | [9 empty] | 2025-03-25 | 2025-04-01 |  |  | 22 | 7 | #NUM! | 0 | 166 |  | 0 | 0 | 0 | 0
| 15 |  | T01: Complex Schedule Generator + Unroll + Unroll | Implement, Verify, Benchmark, and Compare for All of the Operation Specifications for All relevant schedule specifications in SSA form. | [9 empty] | 2025-03-25 | 2025-04-01 |  |  | 22 | 7 | #NUM! | 0 | 167 |  | 0 | 0 | 0 | 0
| 15 |  | T02: Complex Schedule Generator + Split + Split + Split + Split | "" |  |  | 5 | [6 empty] | 2025-03-25 | 2025-04-01 | 2025-04-08 | 2025-04-08 | 22 | 7 | 36 | 0 | 168 |  | 1 | 15 | 0 | 0
| 15 |  | T03: Complex Schedule Generator + Interchange + Interchange + Interchange + Interchange | "" |  |  | 4 | [6 empty] | 2025-03-25 | 2025-04-01 |  |  | 22 | 7 | #NUM! | 0 | 169 |  | 1 | 15 | 0 | 0
| 15 |  | T04: Complex Schedule Generator + Mixed Schedule (length 3) | "" | [9 empty] | 2025-03-25 | 2025-04-01 |  |  | 22 | 7 | #NUM! | 0 | 170 |  | 0 | 0 | 0 | 0
| 15 |  | T05: Complex Schedule Generator + Mixed Schedule (length 4) | "" |  |  | 4 | [6 empty] | 2025-03-25 | 2025-04-01 |  |  | 22 | 7 | #NUM! | 0 | 171 |  | 1 | 15 | 0 | 0
| 15 |  | T06: Complex Schedule Generator + Mixed Schedule (length 5) | "" | [9 empty] | 2025-03-25 | 2025-04-01 |  |  | 22 | 7 | #NUM! | 0 | 172 |  | 0 | 0 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 173 |  | 0 | 0 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 174 |  | 0 | 0 | 0 | 0
Objective E: Performance Analysis | 15 |  | T00: Analysis of Complex Schedule (length 3) | Pick one (1) operation and compare five (5) different schedules of length three (3). Plot all implementations on the same gflops vs size chart. For each implementation perform a bottleneck analysis to determine the reciprocal throughputs (# of cycles between each iteration) for each stage. Plot these rates as a barchart. In the report describe how the bottlenecks move with respect to the schedules. |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 175 |  | 1 | 15 | 0 | 0
| 15 |  | T01: Compare the same schedule across different operations | Pick one (1) schedule of length three (3) and compare five (5) different operation specifications. Plot all implementations on the same gflops vs size chart. For each implementation perform a bottleneck analysis to determine the reciprocal throughputs (# of cycles between each iteration) for each stage. Plot these rates as a barchart. In the report describe how the bottlenecks move with respect to the schedules. |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 176 |  | 1 | 15 | 0 | 0
| 15 |  | T02: Sensitivity Study (vary the factor of a loop split) | Pick one (1) schedule of length three (3) that has a split and compare different split factors (2,4,8,…,step size of the verifier). Plot all implementations on the same gflops vs size chart. For each implementation perform a bottleneck analysis to determine the reciprocal throughputs (# of cycles between each iteration) for each stage. Plot these rates as a barchart. In the report describe how the bottlenecks move with respect to the schedules. This can be repeated for different operations/schedules for additional points |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 177 |  | 1 | 15 | 0 | 0
| 15 |  | T03: Sensitivity Study (vary the architecture) | Pick one (1) schedule of length three (3) one one operation and compare against two (2) different microarchitectures. Plot all implementations on the same gflops vs size chart. For each implementation perform a bottleneck analysis to determine the reciprocal throughputs (# of cycles between each iteration) for each stage. Plot these rates as a barchart. In the report describe how the bottlenecks move with respect to the schedules. This can be repeated for different operations/schedules/architectures for additional points | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 178 |  | 0 | 0 | 0 | 0
| 15 |  | T04: Analysis of Complex Schedule (length 4) | "" |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 179 |  | 1 | 15 | 0 | 0
| 15 |  | T05: Compare the same schedule across different operations | "" |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 180 |  | 1 | 15 | 0 | 0
| 15 |  | T06: Sensitivity Study (vary the factor of a loop split) | "" |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 181 |  | 1 | 15 | 0 | 0
| 15 |  | T07: Sensitivity Study (vary the architecture) | "" | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 182 |  | 0 | 0 | 0 | 0
(Can be repeated for additional points) | 15 |  | T08: Analysis of Complex Schedule (length >4) | Find the best schedule. Repeat the same task that you did for schedules of size 3 and 4. You can repeat this analysis for points for every five (5) new schedules that you analyze. |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 183 |  | 1 | 15 | 0 | 0
| 15 |  | T09: Compare the same schedule across different operations | "" |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 184 |  | 1 | 15 | 0 | 0
| 15 |  | T10: Sensitivity Study (vary the factor of a loop split) | "" |  |  | 6 | [6 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 185 |  | 1 | 15 | 0 | 0
| 15 |  | T11: Sensitivity Study (vary the factor of a loop split for two split factors) | "" | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 186 |  | 0 | 0 | 0 | 0
| 15 |  | T12: Sensitivity Study (vary the architecture) | "" | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 187 |  | 0 | 0 | 0 | 0
| 20 |  | T13: Post your best performance plot and schedule on canvas | On canvas post your best implementations. Teams can post multiple times. The goal is to crowdsource the best schedule for a given operation and architecture combination | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 188 |  | 0 | 0 | 0 | 0
|  | 25 | TXX-Opt00: Automate the extraction of the reciprocal throughput for fetch | Create a program that calculates how many cycles elapses between a full iteration being fetched. This can either extract the byte information from the objdump report or you can create your own instruments using C label pointers to compute the address of the start and end of the block (https://gcc.gnu.org/onlinedocs/gcc-4.3.4/gcc/Labels-as-Values.html) | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 189 |  | 0 | 0 | 0 | 0
|  | 25 | TXX-Opt01: Automate the extraction of the reciprocal throughput for decode | Create a program that extracts the decode rate from the osaca or mca reports | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 190 |  | 0 | 0 | 0 | 0
|  | 25 | TXX-Opt02: Automate the extraction of the reciprocal throughput for execution stage | Create a program that extracts the maximum reciprocal throughput across all execution units of the process from osaca or mca. | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 191 |  | 0 | 0 | 0 | 0
|  | 25 | TXX-Opt03: Automate the extraction of the number of L1 instruction, L1 data and last level cache (llc) read misses | Create a program that extracts the number of read misses | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 192 |  | 0 | 0 | 0 | 0
|  | 25 | TXX-Opt04: Bar Plot tool for reciprocal throughputs | Create a tool that creates bar plots for comparing reciprocal throughputs (F,D&E) against 1 or more implementations. | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 193 |  | 0 | 0 | 0 | 0
|  | 25 | TXX-Opt05: Bar plot tool for cache misses | Create a tool that creates bar plots for cache misses (L1D,L12I,LLC) against 1 or more implementations. | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 194 |  | 0 | 0 | 0 | 0
|  | 50 | TXX-Opt06: Schedule generator | Create a tool that generates all valid schedules for a given length | [9 empty] | 2025-04-01 | 2025-04-08 |  |  | 29 | 7 | #NUM! | 0 | 195 |  | 0 | 0 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 220 |  | 0 | 0 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 221 |  | 0 | 0 |  | 0
Part 3 | Points Required | Points Optional | [15 empty] | #NUM! | 0 | #NUM! | 0 | 222 |  |  |  | 0
Final Writeup | [17 empty] | #NUM! | 0 | #NUM! | 0 | 223 |  | 0 | 0 | 0 | 0
|  |  | Writeup ./lab/docs/final-report.pdf [approx6-8 pages, but more can be used. 2-column in LaTeX] | LaTeX document built from the working technical document that conveys the problems you solved and how. | writeup.pdf | [12 empty] | #NUM! | 0 | #NUM! | 0 | 224 |  |  | 0 | 0 | 0
| 20 |  | Section: Introduction | Additional questions: What is the problem? Why is hard? Why does it matter (with examples)? How do you solve it? What were the high level results? |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 225 |  | 1 | 20 | 0 | 0
| 20 |  | Section: Objective A | Additional Questions: How did the implementations differ in terms of algorithms? How they accessed their data? How they used the underlying Resources? In the case of the C code, how the generated assembly differs (https://godbolt.org/ will let you evaluate different compilers)? How did the performance differ and why? |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 226 |  | 1 | 20 | 0 | 0
| 20 |  | Section: Objective B | additional questions: What are trying to do? How do you solve it? What is the design (figures,pseudocode,algorithms,code listings)? What were the results? What do take from these results and why? |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 227 |  | 1 | 20 | 0 | 0
| 20 |  | Section: Objective C | additional questions: What are trying to do? How do you solve it? What is the design (figures,pseudocode,algorithms,code listings)? What were the results? What do take from these results and why? |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 228 |  | 1 | 20 | 0 | 0
| 20 |  | Section: Objective D | additional questions: What are trying to do? How do you solve it? What is the design (figures,pseudocode,algorithms,code listings)? What were the results? What do take from these results and why? |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 229 |  | 1 | 20 | 0 | 0
| 20 |  | Section: Objective E | Provide your performance and sensitivity plots along with your analysis. |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 230 |  | 1 | 20 | 0 | 0
| 20 |  | Summary | recap of what you did and ideas for future directions |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 231 |  | 1 | 20 | 0 | 0
| 20 |  | References | Bibliography |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 232 |  | 1 | 20 | 0 | 0
|  | 5 | Appendix | Attempts and refinements should be described here. |  |  | 1 | [6 empty] | 2025-04-01 | 2025-04-08 | 2025-04-07 | 2025-04-09 | 29 | 7 | 35 | 2 | 233 |  | 1 | 5 | 0 | 0
[18 empty] | #NUM! | 0 | #NUM! | 0 | 234
[18 empty] | #NUM! | 0 | #NUM! | 0 | 235
Required Points: | 1230
Available | 1500
Estimated Raw Points | 820
TA/Instructor Raw Points | 0
Formulas:
Est Start Date = [Est Start Date, row above]
Est Start Date = [Est Start Date, row above]+7
Est end = [Est Start Date]+1
Est end = [Est end, row above]
Est Start Day (Day=1 first day of lab) = DATEDIF(Summary!$B7,[Est Start Date],"d")+1
Est Duration = DATEDIF([Est Start Date],[Est end],"d")
Actual duration = DATEDIF([Act Start Date],[Act End Date],"d")

## Project Planner
Project Planner
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235 | 71 | 72 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100 | 101 | 102 | 103 | 104 | 105 | 106 | 107 | 108 | 109 | 110 | 111 | 112 | 113 | 114 | 115 | 116 | 117 | 118 | 119 | 120 | 121 | 122 | 123 | 124 | 125 | 126 | 127 | 128 | 129 | 130 | 131 | 132 | 133 | 134 | 135 | 136 | 137 | 138 | 139 | 140 | 141 | 142 | 143 | 144 | 145 | 146 | 147 | 148 | 149 | 150 | 151 | 152 | 153 | 154 | 155 | 156 | 157 | 158 | 159 | 160 | 161 | 162 | 163 | 164 | 165 | 166 | 167 | 168 | 169 | 170 | 171 | 172 | 173 | 174 | 175 | 176 | 177 | 178 | 179 | 180 | 181 | 182 | 183 | 184 | 185 | 186 | 187 | 188 | 189 | 190 | 191 | 192 | 193 | 194 | 195 | 196 | 197 | 198 | 199 | 200 | 201 | 202 | 203 | 204 | 205 | 206 | 207 | 208 | 209 | 210 | 211 | 212 | 213 | 214 | 215 | 216 | 217 | 218 | 219 | 220 | 221 | 222 | 223 | 224 | 225 | 226 | 227 | 228 | 229 | 230 | 231 | 232 | 233 | 234 | 235
Communication | 1 | 1 | 1 | 0 | 100%
Version Control System | 1 | 1 | 1 | 0 | 100%
Configure IDE | 1 | 1 | 1 | 0 | 100%
Initial Build | 1 | 1 | 1 | 0 | 100%
Review Lab Document | 1 | 2 | 1 | 2 | 0%
Initial Statement of Work (wk 1) | 1 | 7 | 1 | 7 | 0%
One page slide (wk 1) | 1 | 7 | #NUM! | 0 | 0%
Tasksheet (wk 1) | 1 | 7 | #NUM! | 0 | 0%
One page slide (wk 2) | 8 | 7 | 8 | 7 | 100%
Tasksheet (wk 2) | 8 | 7 | 8 | 7 | 100%
One page slide (wk 3) | 15 | 7 | #NUM! | 0 | 0%
Tasksheet (wk 3) | 15 | 7 | #NUM! | 0 | 0%
One page slide (wk 4) | 22 | 7 | 22 | 0 | 100%
Tasksheet (wk 4) | 22 | 7 | 22 | 0 | 100%
Update final statement of work | 29 | 7 | 29 | 7 | 100%
Submit final codebase | 29 | 7 | 37 | 0 | 100%
Submit final document | 29 | 7 | 37 | 0 | 100%
submit additional material | 29 | 7 | #NUM! | 0 | 0%
Submit final tasksheet | 29 | 7 | 37 | 0 | 100%
Submit team assessment | 29 | 7 | 37 | 0 | 100%
0 | #NUM! | 0 | #NUM! | 0 | 0%
Task Name | #NUM! | 0 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
Initial Outline for technical writeup | 1 | 7 | #NUM! | 0 | 100%
Working Draft (wk 2) | 8 | 7 | #NUM! | 0 | 100%
Updated Working Draft (wk 3) | 15 | 7 | #NUM! | 0 | 100%
Updated Working Draft (wk 4) | 22 | 7 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
.gitlab-ci.yml | #NUM! | 0 | #NUM! | 0 | 0%
deploy runners on OU resources | #NUM! | 0 | #NUM! | 0 | 0%
Implement directory structure for lab | 1 | 3 | #NUM! | 0 | 100%
Implement top-level driver scripts that runs all objective scripts | 1 | 3 | #NUM! | 0 | 100%
Implement Objective-level driver scripts that run all tasks scripts | 1 | 3 | #NUM! | 0 | 100%
0 | 1 | 3 | #NUM! | 0 | 0%
Implement task-level driver scripts for objective a for running the code | 1 | 3 | #NUM! | 0 | 100%
Implement task-level driver scripts for objective b for running the generators and evaluating the resulting code | 1 | 3 | #NUM! | 0 | 100%
Implement task-level driver scripts for objective c for running the generators and evaluating the resulting code | 1 | 3 | #NUM! | 0 | 100%
Implement task-level driver scripts for objective d for running the generators and evaluating the resulting code | 1 | 3 | #NUM! | 0 | 100%
Implement task-level driver scripts for objective d for running the generators and evaluating the resulting code | 1 | 3 | #NUM! | 0 | 100%
0 | #NUM! | 0 | #NUM! | 0 | 0%
Design the baseline generator | 1 | 7 | #NUM! | 0 | 100%
Design the baseline generator + unroll | 1 | 7 | #NUM! | 0 | 100%
Design the baseline generator + split | 1 | 7 | #NUM! | 0 | 100%
Design the baseline generator + interchange | 1 | 7 | #NUM! | 0 | 100%
0 | #NUM! | 0 | #NUM! | 0 | 0%
Design the AST to C code generator | 8 | 7 | #NUM! | 0 | 100%
Design and implement unit tests for AST to C code generator that cover 100% of your code. | 8 | 7 | #NUM! | 0 | 0%
Implement and test AST node for: function | 8 | 7 | #NUM! | 0 | 100%
Implement and test AST node for: loop | 8 | 7 | #NUM! | 0 | 100%
Implement and test AST node for: assign to a variable and assign to memory location | 8 | 7 | #NUM! | 0 | 100%
Implement and test AST node for: add, multiply and modulo | 8 | 7 | #NUM! | 0 | 100%
Implement and test AST node for: less-than | 8 | 7 | #NUM! | 0 | 100%
Design the Objective Specification to AST functionality | 8 | 7 | #NUM! | 0 | 100%
Design and implement unit tests for Operation Specification to AST | 8 | 7 | #NUM! | 0 | 0%
Design the compiler pass (AST to AST) for implementing unroll | 8 | 7 | #NUM! | 0 | 0%
Design the unit tests for the unroll pass | 8 | 7 | #NUM! | 0 | 0%
Design the compiler pass (AST to AST) for implementing split | 8 | 7 | #NUM! | 0 | 0%
Design the unit tests for the split pass | 8 | 7 | #NUM! | 0 | 0%
Design the compiler pass (AST to AST) for implementing interchange | 8 | 7 | #NUM! | 0 | 0%
Design the unit tests for the interchange pass | 8 | 7 | #NUM! | 0 | 0%
Design the generalized scheduler (AST to AST) | 15 | 7 | #NUM! | 0 | 0%
Design the unit tests for the unroll pass using the generalized scheduler | 15 | 7 | #NUM! | 0 | 0%
Design the unit tests for the split pass using the generalized scheduler | 15 | 7 | #NUM! | 0 | 0%
Design the unit tests for the interchange pass using the generalized sheduler | 15 | 7 | #NUM! | 0 | 0%
Design the unit tests for verifying complex (more than one transformation) schedules | 15 | 7 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
Task Name | #NUM! | 0 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
T00: Handspun Baseline | 1 | 7 | 1 | 7 | 100%
T01: Handspun + Unroll | 1 | 7 | 1 | 7 | 100%
T01-Opt00: Handspun + Unroll( r) vs Unroll ( q) | 1 | 7 | 1 | 7 | 100%
T02: Handspun + Split | 1 | 7 | 1 | 21 | 100%
T02-Opt00: Handspun + Split(i) vs Split (j) vs Split(q) vs Split( r) | 1 | 7 | 1 | 21 | 100%
T02-Opt01: Handspun + Split(2) vs +Split(4) vs Split(8) | 1 | 7 | 1 | 7 | 100%
T03: Handspun + Interchange | 1 | 7 | 1 | 7 | 100%
T04: Handspun + Complex Schedule (3 Commands) | 1 | 7 | 1 | 7 | 100%
T04-Opt00: Handspun + Complex Schedule (3 Commands) | 1 | 7 | 1 | 7 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
T00: Simple Standalone Baseline | 8 | 7 | 8 | #NUM! | 0%
T01: Simple Standalone + Unroll v1 | 8 | 7 | 8 | #NUM! | 100%
T02: Simple Standalone + Split | 8 | 7 | 22 | 2 | 100%
T03: Simple Standalone + Interchange | 8 | 7 | 8 | #NUM! | 100%
0 | #NUM! | 0 | #NUM! | 0 | 0%
T00: Implement AST to C codegen | 15 | 7 | #NUM! | 0 | 0%
T01: Implement Operation Specification to AST | 15 | 7 | #NUM! | 0 | 0%
T02: Implement the compiler pass (AST to AST) for implementing unroll | 15 | 7 | #NUM! | 0 | 0%
T03: Implement the compiler pass (AST to AST) for implementing split | 15 | 7 | #NUM! | 0 | 0%
T04: Implement the compiler pass (AST to AST) for implementing interchange | 15 | 7 | #NUM! | 0 | 0%
T05: EoC Standalone Baseline | 15 | 7 | 24 | 7 | 100%
T06: EoC Standalone + Unroll | 15 | 7 | #NUM! | 0 | 100%
T07: EoC Standalone + Split | 15 | 7 | 36 | 0 | 100%
T08: EoC Standalone + Interchange | 15 | 7 | #NUM! | 0 | 100%
0 | #NUM! | 0 | #NUM! | 0 | 0%
T00: Implement Generalized Schedule (AST to AST) | 22 | 7 | #NUM! | 0 | 0%
T01: Complex Schedule Generator + Unroll + Unroll | 22 | 7 | #NUM! | 0 | 0%
T02: Complex Schedule Generator + Split + Split + Split + Split | 22 | 7 | 36 | 0 | 100%
T03: Complex Schedule Generator + Interchange + Interchange + Interchange + Interchange | 22 | 7 | #NUM! | 0 | 100%
T04: Complex Schedule Generator + Mixed Schedule (length 3) | 22 | 7 | #NUM! | 0 | 0%
T05: Complex Schedule Generator + Mixed Schedule (length 4) | 22 | 7 | #NUM! | 0 | 100%
T06: Complex Schedule Generator + Mixed Schedule (length 5) | 22 | 7 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
T00: Analysis of Complex Schedule (length 3) | 29 | 7 | #NUM! | 0 | 100%
T01: Compare the same schedule across different operations | 29 | 7 | #NUM! | 0 | 100%
T02: Sensitivity Study (vary the factor of a loop split) | 29 | 7 | #NUM! | 0 | 100%
T03: Sensitivity Study (vary the architecture) | 29 | 7 | #NUM! | 0 | 0%
T04: Analysis of Complex Schedule (length 4) | 29 | 7 | #NUM! | 0 | 100%
T05: Compare the same schedule across different operations | 29 | 7 | #NUM! | 0 | 100%
T06: Sensitivity Study (vary the factor of a loop split) | 29 | 7 | #NUM! | 0 | 100%
T07: Sensitivity Study (vary the architecture) | 29 | 7 | #NUM! | 0 | 0%
T08: Analysis of Complex Schedule (length >4) | 29 | 7 | #NUM! | 0 | 100%
T09: Compare the same schedule across different operations | 29 | 7 | #NUM! | 0 | 100%
T10: Sensitivity Study (vary the factor of a loop split) | 29 | 7 | #NUM! | 0 | 100%
T11: Sensitivity Study (vary the factor of a loop split for two split factors) | 29 | 7 | #NUM! | 0 | 0%
T12: Sensitivity Study (vary the architecture) | 29 | 7 | #NUM! | 0 | 0%
T13: Post your best performance plot and schedule on canvas | 29 | 7 | #NUM! | 0 | 0%
TXX-Opt00: Automate the extraction of the reciprocal throughput for fetch | 29 | 7 | #NUM! | 0 | 0%
TXX-Opt01: Automate the extraction of the reciprocal throughput for decode | 29 | 7 | #NUM! | 0 | 0%
TXX-Opt02: Automate the extraction of the reciprocal throughput for execution stage | 29 | 7 | #NUM! | 0 | 0%
TXX-Opt03: Automate the extraction of the number of L1 instruction, L1 data and last level cache (llc) read misses | 29 | 7 | #NUM! | 0 | 0%
TXX-Opt04: Bar Plot tool for reciprocal throughputs | 29 | 7 | #NUM! | 0 | 0%
TXX-Opt05: Bar plot tool for cache misses | 29 | 7 | #NUM! | 0 | 0%
TXX-Opt06: Schedule generator | 29 | 7 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
Writeup ./lab/docs/final-report.pdf [approx6-8 pages, but more can be used. 2-column in LaTeX] | #NUM! | 0 | #NUM! | 0 | 0%
Section: Introduction | 29 | 7 | 35 | 2 | 100%
Section: Objective A | 29 | 7 | 35 | 2 | 100%
Section: Objective B | 29 | 7 | 35 | 2 | 100%
Section: Objective C | 29 | 7 | 35 | 2 | 100%
Section: Objective D | 29 | 7 | 35 | 2 | 100%
Section: Objective E | 29 | 7 | 35 | 2 | 100%
Summary | 29 | 7 | 35 | 2 | 100%
References | 29 | 7 | 35 | 2 | 100%
Appendix | 29 | 7 | 35 | 2 | 100%
0 | #NUM! | 0 | #NUM! | 0 | 0%
0 | #NUM! | 0 | #NUM! | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%
0 | 0 | 0 | 0 | 0 | 0%

## Attendance
Notes: | 0 | While I take attendance every day, it's possible that I missed you. This is to prevent you from losing points. Managers will fill this out.
| 1 | If you were absent (or >15 min late), then please fill out an absence form for each day that you were out.
| 2 | For each day mark with a 1 if the member was present. Late (>15min <30min) with a .5, and 0 if you were >30min late or absent.
| 4 | If a member missed a day, but submitted an absence sheet, then still mark the day as 0. We will adjust in the backend
| 5 | Make sure to submit an absence sheet (on canvas) if you miss class. You have 2 freebie unexcused absences.
| In-class lab day | Member A | Member B | Member C | Member D | Member E | Member F
Thursday | 1 | 1 | 1 | 1 | 1 | 1 | 1
Tuesday | 2 | 1 | 1 | 1 | 1 | 1 | 1
Thursday | 3 | 1 | 1 | 1 | 1 | 1 | 1
Tuesday | 4 | 1 | 1 | 1 | 1 | 1 | 1
Thursday | 5 | 0 | 0 | 1 | 1 | 1 | 1
Tuesday | 6 | 1 | 1 | 1 | 1 | 1 | 1
Thursday | 7 | 1 | 1 | 1 | 1 | 1 | 1
Tuesday | 8 | 1 | 0 | 1 | 1 | 1 | 1
Thursday | 9 | 1 | 1 | 1 | 1 | 1 | 1
Tuesday | 10 | 1 | 1 | 1 | 1 | 1 | 1
Thursday | 11 | 1 | 0 | 0 | 1 | 1 | 1
Tuesday | 12 | 1 | 1 | 1 | 1 | 1 | 1
Totals |  | 11 | 9 | 11 | 12 | 12 | 12

## Effort %
| 0 | The TA and Instructor will this part out from your self-assessments
Notes: | 1 | How you and your team decides to divide up contribute is up to you.
| 2 | Each member will have a column attributing a percentage of effort for each member (row)
| 3 | The default values here will change according to your assessments.
|  | Member A | Member B | Member C | Member D | Member E | Member F |  | 2 Member Avg | 3 Member Avg | 4 Member Avg | 5 Member Avg | 6 Member Avg
| Member A (manager) | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | Member A (manager) | 0.15 | 0.15 | 0.15 | 0.15 | 0.18
| Member B (tech lead) | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | 0.18 | Member B (tech lead) | 0.18 | 0.18 | 0.18 | 0.18 | 0.216
| Member C | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | 0.16 | Member C |  | 0.16 | 0.16 | 0.16 | 0.192
| Member D | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | Member D |  |  | 0.19 | 0.19 | 0.228
| Member E | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | Member E |  |  |  | 0.19 | 0.228
| Member F | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | 0.19 | Member F |  |  |  |  | 0.228
| Sum (should be 1 or 0) | 1.06 | 1.06 | 1.06 | 1.06 | 1.06 | 1.06

## Scoring
Notes | 0 | This sheet is for the TA/Instructor to fill out.
| 1 | It is included to show how the final scores are calculated
| 2 | The numbers you see here do not constitute your final grade.
3
General premise on grading
| 0 | All points that are validated are summed up as raw team points
| 1 | Each member will get a certain percentage of those points
| 2 | That percentage is based on the average of a members effort
| 3 | Effort precentages will be provided via an individual submission on canvas
| 4 | The individual points received will be the raw points scaled by that average and converted into a grade between 0%-100%
| 5 | From that score managers and tech leads will get an additional bonus
| 6 | Similarly, for each day missed we will subtract (100/number of days) points from the score.
| 7 | All individual scores will be fixed between 0 and 100%
| 8 | There may be bugs and typos in this sheet that we have correct. At the end of the day we are implementing the policy listed above.
| 9 | While this seems complex, as long as you attend class and work you will do well.
Estimated Raw Points | 1020
TA/Instructor | 0
Use Estimated | 1 | set to 1 to use estimated value, 0 otherwise. This will give you an upper estimate.
Use TA/Instructor | 0 | set to 1 to use estimated value, 0 otherwise. This is what we will use to grade.
Raw points | 1020
Absence Penalty | 8.3333
Missed Days
Member A (manager) | 1
Member B (tech lead) | 3
Member C | 1
Member D | 0
Member E | 0
Member F | 0
Missed Day Penalty
Member A (manager) | -8.3333
Member B (tech lead) | -25
Member C | -8.3333
Member D | 0
Member E | 0
Member F | 0
Role Bonuses
Member A (manager) | 25
Member B (tech lead) | 25
Member C | 0
Member D | 0
Member E | 0
Member F | 0
Proportion of points | 2 Member | 3 Member | 4 Member | 5 Member | 6 Member
Member A (manager) | 153 | 153 | 153 | 153 | 183.6
Member B (tech lead) | 183.6 | 183.6 | 183.6 | 183.6 | 220.32
Member C | 0 | 163.2 | 163.2 | 163.2 | 195.84
Member D | 0 | 0 | 193.8 | 193.8 | 232.56
Member E | 0 | 0 | 0 | 193.8 | 232.56
Member F | 0 | 0 | 0 | 0 | 232.56
Per-Person point thresholds | 246 | 246 | 246 | 243 | 243
Points to grade (pre bonus/penalty) | 2 Member | 3 Member | 4 Member | 5 Member | 6 Member
Member A (manager) | 62.1951 | 62.1951 | 62.1951 | 62.963 | 75.5556
Member B (tech lead) | 74.6341 | 74.6341 | 74.6341 | 75.5556 | 90.6667
Member C | 0 | 66.3415 | 66.3415 | 67.1605 | 80.5926
Member D | 0 | 0 | 78.7805 | 79.7531 | 95.7037
Member E | 0 | 0 | 0 | 79.7531 | 95.7037
Member F | 0 | 0 | 0 | 0 | 95.7037
Grade with Bonus and Penalty | 2 Member | 3 Member | 4 Member | 5 Member | 6 Member
Member A (manager) | 78.8618 | 78.8618 | 78.8618 | 79.6296 | 92.2222
Member B (tech lead) | 74.6341 | 74.6341 | 74.6341 | 75.5556 | 90.6667
Member C |  | 58.0081 | 58.0081 | 58.8272 | 72.2593
Member D |  |  | 78.7805 | 79.7531 | 95.7037
Member E |  |  |  | 79.7531 | 95.7037
Member F |  |  |  |  | 95.7037